## Aktivitäten GenE
Generation Europe | January |  | February |  | March | April | May |  | June | July |  | August | September |  | October |  | November |  | December
2018
Level of youth policy | [9 empty] | Transnational Meeting | Meeting international Stakeholders | Transnational Meeting | 1st Meeting Steering Commitee | Transnational Meeting
Youth project | [9 empty] | Kick Off Conference |  | Local Meetings (Thematic Introduction) | Training | Work Meeting Method Box | 1st Youth Encounter (Active Citizenship, basic human rights, Democracy) |  | Local Meetings (Problem identification on local level) | Work Meeting Digital Platform
2019
Level of youth policy |  |  | 2nd Meeting Steering Commitee |  |  | Transnational Meeting |  |  | Transnational Meeting | [5 empty] | Politic discusses with youths & Meeting international Stakeholders
Youth project | Local Meetings (Problem identification on local level) |  | Preparatory Meeting Method Workshop |  | Method Workshop | Local Meetings (Research and Discourse on local level) | Work Meeting Digital Platform |  |  | 2nd Youth Encounter (Connection local and international level, Empowerment) |  |  | Local Meetings (Development Action Plans) |  | Work Meeting Method Box | Youth conference (Training, Campaigning and youth discusses with politic) | Local Meetings (Implementation Action Plans) |  | Local Meetings (Implementation Action Plans)
2020
Level of youth policy |  |  | 3rd Meeting Steering Commitee | Transnational Meeting |  |  | Transnational Meeting | Transnational Meeting | [6 empty] | Meeting international Stakeholders |  |  |  | 4th Meeting Steering Commitee
Youth project | Work Meeting Digital Platform | Local Meetings (Implementation Action Plans, Meeting Politic on local and european level) | Preparatory Meeting Method Workshop |  | Method Workshop | Local Meetings (Implementation Action Plans) | Local Meetings (Implementation Action Plans) |  |  | 3rd Youth Encounter (Medial Products, Reflection, Development of perspectives) |  |  | European Action Week (Decentral Presentation of all youth projects) | Final Meeting Method Box | Final Event professional level (conference) | Work Meeting Digital Platform | Local Meetings (Evaluation and Development of Perspectives)
Level of youth policy
Activities professionals
Activities youths